## Time Estimates
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment | Task No. | Details of Task | Estimated Time
[6 empty] | 1 | Create a time_Estimate and task breakdown analysis and share with team via channels or Jira to aid collaboration and accountability. | 1 hour
[6 empty] | 2 | Implement product microservices using the MockAPI examples. | 15 mins
[6 empty] | 3 | Implement order microservices using the MockAPI examples. | 15 mins
[6 empty] | 4 | Create schema and upload the data to Weaviate. Partition the order collection by product category. | 30 mins
[6 empty] | 5 | Create a flowchart of intended implementation of chatbot service. | 1 hour
[6 empty] | 6 | Perform prompt engineering as required by the different areas of the flowchart. | 30 mins
[6 empty] | 7 | Implement function to extract logical filter and sort constraints from a natural language query using LLM. | 30 mins
[6 empty] | 8 | Implement class for basic memory/history of chats. | 15 mins
[6 empty] | 9 | Implement functions for retrieval of data from vector DB and MongoDB. | 1 hour
[6 empty] | 10 | Implement functions to aid in correct generation of LLM response. | 1 hour
[6 empty] | 11 | Implement RAG function to combine the above chatbot functionalities | 15 mins
[6 empty] | 12 | Implement testing for the chatbot, order, and product services. | 1 hour
[6 empty] | 13 | Solve any eventual bugs and deploy backend to Render. | 45 mins
[6 empty] | 14 | Implement React UI for the API and chatbot services. | 1.5 hours
[6 empty] | 15 | Integrate the UI with the backend and solve any eventual bugs. | 1 hour
[6 empty] | 16 | Deploy to Vercel or alternative. | 15 mins
[6 empty] | 17 | Add ReadMe for both frontend and backend and cover. | 30 mins